## Slide 1: PowerPoint 13: 4.11 Procedure for handing over projects to clients
4: Construction and the built environment industry

## Slide 2: When the project is finished
Successful completion of a project is followed by the handover of the building to the client.
This must be done in accordance with procedures sometimes referred to as ‘closing out’ the construction phase prior to occupation and use of the building.
In this session, we will look at the way the handover process is arranged, and the methods used to make the process as smooth as possible.

## Slide 3: Key phases
Construction. Construction of the building according to the predetermined work programme. The client is kept informed about progress and project details throughout the process.
Handover and close-out. The contractor works closely with the client to bring the completed building into use as smoothly as possible.
In use/occupation. The client takes up responsibility for operational management of the building.

## Slide 4: Handover documentation
Health and safety file. Safe operation and user welfare information.
Building owner’s manual. Overview of operational information.
User guide. Day-to-day operational support.
Building logbook (passport). Record of important events in the building’s lifecycle so far.
Testing and commissioning documents. Lifts, elevators, lifting equipment, cradles and cleaning access equipment, boilers and pressure vessels, electrical installation schedule of inspections, schedule of test results.
Warranties. Agreed and contracted guarantee arrangements.
For a large project there will be a substantial amount of documentation involved to inform and support the client and to discharge the contractors' responsibilities, including the following.

## Slide 5: Snagging
After handover, it is possible that further faults will be identified which the contactor will be called upon to deal with.
‘Snagging’ is the term used to identify and rectify faults and flaws in the building. This is an ongoing process throughout the construction phase with a final round of snagging before handover.
A defects reporting procedure between the client and the contractor is agreed at handover.
Access arrangements will be agreed to allow the contractor to enter the building to undertake the necessary remedial work while the facility is in use.

## Slide 6: Additional factors
The expression ‘soft landings’ is increasingly used to describe the smooth handover of a project between the contractor and the client.
The concept aims to remove the ‘bumps’ that can occur in the transition period and after-care arrangements, to ensure operational performance of the building is optimised for the users.
The building must operate well to fulfil the client’s requirements.

## Slide 7: Additional factors (continued)
Some factors that must be cared for to ensure a smooth handover include the following.
  Transfer of insurance responsibility from contractor to client/occupier.
  Security responsibility for the building to be transferred to client/occupier.
  Legal adoption of roads and access ways should be signed.
  Outsourced contracts for maintenance and inspections should be signed.
At handover, the formation of a client operation team should take place to ensure the building is equipped as designed and operating as planned.

## Slide 8
Any questions?