## Slide 1: PowerPoint 7: Gantt charts and critical path networks
8. Construction information and data principles
8.2 Sources of information

## Slide 2
Named after Henry Gantt, an American mechanical engineer and social scientist, a Gantt chart is a horizontal bar chart used in project management to visually represent a project plan over time. A quick glance at a Gantt chart typically shows the timeline and status for each task in a project:
when each task will begin and end
how long each task will take
who is assigned to each task
how tasks relate to and depend on each other
how work is progressing in a project
the full project schedule from start to finish.
This is a way to communicate what it will take to deliver a project on time and on budget.
What is a Gantt chart?

## Slide 3: Use of Gantt charts
Gantt charts are used for planning and scheduling projects in project management. A Gantt chart is incredibly useful because it allows you to:
simplify complex projects into an easy-to-follow, colour-coded plan
track the status of tasks as work progresses
help keep track of project deadlines, milestones and hours worked so you can spot and address delays
add detail such as the team responsible for each stage, links or interdependencies between stages (shown with interconnecting lines), and key project milestones.

## Slide 4
PowerPoint presentation
Gantt chart example

## Slide 5: Critical path method (CPM)
The critical path method (CPM) dates from the 1950s but is still widely used. A critical path is a visual representation of project tasks and the time required to complete each one.
Each task can be represented by a node (shape). Nodes are tied together with lines or arrows representing the sequence between tasks. This approach is referred to as the activity-on-node (AON).
CPM is a step-by-step project management technique to identify activities on the critical path. It breaks a project into work tasks in a flow chart, and calculates the project duration based on estimated time frames for each task. It also identifies tasks that are time critical.

## Slide 6: CPM example: assembling a train set

## Slide 7: Steps to drawing the critical path
Step 1: Specify each activity
Identify the main deliverables of a project and each activity (or task) involved in the project. This list should only include higher-level activities so the critical path is not too detailed and complex to manage.
Display your work breakdown as a tree structure, lists or tables.
Step 2: Establish dependencies (activity sequence)
Some activities depend on the completion of others. To correctly identify activities and their precedence, ask yourself these three questions for each activity on your list:
Which task should take place before this task happens?
Which tasks should be finished at the same time as this task?
Which tasks should happen right after this task?

## Slide 8: Drawing the critical path
Step 3: Draw the network diagram
Once the activities and their dependencies have been identified, the critical path analysis chart (CPA), known as the network diagram can be drawn. There are software programs that can create this diagram.

## Slide 9: Drawing the critical path
Step 4: Estimate activity completion time
Depending in the project, tasks can be estimated in weeks or days. To ensure accuracy, the three-point estimation method requires three time estimates for every task, based on prior experience or best guesses.
E stands for estimate
a = the best-case estimate (eg 2 days) m = the most likely estimate (eg 4 days) b = the worst-case estimate (eg 6 days)
Divide by 3 (the three-point estimation method)
E = (a + m + b)/3
E= (2 days + 4 days + 6 days)/3
E = 4 days

## Slide 10: Drawing the critical path
Step 5: Identify the critical path
Your network diagram shows the longest path throughout the network (by adding the days noted in the boxes). If you have multiple critical paths, you will run into network sensitivity, meaning that the critical path is likely to change once the project begins. The more critical paths in a project, the higher the probability of a change in schedule.

## Slide 11: Benefits of CPM
Identifies the most important tasks: allows you to identify the key milestones in a project.
Reduces risk and uncertainty: calculating the shortest and longest completion time of each activity and considering unexpected factors identifies the risks to be managed.
Helps reduce timelines: it is easy to identify where the tasks fall in the overall timeframe which provides a new level of insight into your project’s timeline.
Compares planned with actual: the baseline schedule developed from the initial critical path analysis can be used to track schedule progress. A project manager can identify tasks completed, predict durations for in-progress tasks, and anticipate changes to future task sequences and durations.

## Slide 12: Carbon emission data
Emissions from the construction industry reached the highest ever level in 2019, according to a report published by the United Nations Environment Programme.
According to the report, energy-related carbon emissions increased by 9.95 gigatonnes in 2019.
When adding emissions from the building construction industry on top of operational emissions, the sector accounted for 38% of total global energy-related emissions.
In order to reach net zero, the International Energy Agency (IEA) has estimated that emissions generated by the building industry need to fall by 50% by 2030. This equates to around 6% per year.
Notes: For more information see Construction industry accounts for 38% of CO2 emissions – EnvironmentJournal

## Slide 13: Understanding carbon emission data
Six materials cause 70% of carbon emissions. For example, the 4 billion tonnes of cement produced each year for concrete construction accounts for 8% of total global carbon emissions.
It is therefore important to be able to understand the data on carbon emissions to be fully informed. To look at the latest emissions data, see Final UK greenhouse gas emissions national statistics: 1990 to 2019 - GOV.UK (www.gov.uk).
It is also important to identify carbon-embodied materials and analyse product data to select lower carbon alternatives if available.

## Slide 14
Any questions?