## Slide 1: PowerPoint 6: 4.4 Procurement of projects within the construction sector
4: Construction and the built environment industry

## Slide 2: Defining procurement
Procurement is the process through which goods or services for a construction project are sourced and purchased.
The process of procurement can be referred to as a ‘route’. There are many different routes or paths that can be followed to finalise a contract.
The procurement route followed can be influenced by the scale and type of project. This can be categorised as domestic, commercial or industrial and this categorisation will determine how the needs and demands of the client are matched to the procurement route.
In this session we will consider the common factors and stages in the procurement process and identify the different routes that can be taken.

## Slide 3
Common factors in procurement
  The client may not award the contract based solely on the lowest costed tender submitted. An important consideration that will influence the decision on awarding a contract is the reputation of the contractor in terms of successful delivery of previous projects.
  Tendering and bidding
  For a larger project, it may be that several contractors will compete or ‘bid’ to secure the contract.
  This process is referred to as a ‘tender’. The client then decides which contractor they wish to use.
  Each contractor makes calculations of resource requirements for a project and the timescales over which the work will be completed.

## Slide 4
Common factors in procurement (continued)
  Tenders can be described as ‘open’ or ‘closed’.
  An open tender (sometimes called a competitive or public tender) will allow all qualified bidders to submit an entry.
  A closed tender is where only invited contractors can submit a bid for consideration by the client. This means that only contractors who the client views as having a good reputation will be able to submit a tender.
  The sealed bids are opened in public and the client chooses on the basis of price and quality. This means contractors are focused on offering a bid that is as attractive as possible to the client.

## Slide 5
Common factors in procurement (continued)
  Elements of the tender
  Pre-tender planning. The part of the process before the tender is prepared. Does the contractor have the resources and personnel to take on the project ? Can they complete the build within the timescale?
  Pre-contract planning. Before the contract is written. The contractor may have up to six weeks to plan things such as the site layout, laying on of temporary services and preparation of the work programme.

## Slide 6
Common factors in procurement (continued)
  Elements of the tender (continued)
  Estimate. Essentially a best guess of how much a specific project will cost or how long it will take to complete. The job could cost more or less than the estimated cost.
  Quote. A promise to complete the work at an agreed price setting out the specific work that will be done.
  Provisional sum. Work for which there is no accurate quote or estimate.
  Preliminaries. Costs that are incurred before the actual construction of a building begins such as management and supervision costs and setting-up costs.

## Slide 7
Common factors in procurement (continued)
  Prime cost. Amounts to cover work undertaken by separate contractors such as laying on services to site such as electricity or water.
  Elements of the tender (continued)
  Overheads. Costings to cover on-going items such as insurance costs, plant and equipment depreciation.
  Contingencies. A percentage added to cover unforeseen costs that may arise throughout the duration of the contract.

## Slide 8
Types of procurement routes
  Contractor led. The contractor provides a team to develop the concept from the client brief as part of the procurement process.
  Fast track. Used mainly for construction management contracts. This type of procurement route overlaps the design and construction phase of the project to reduce the overall duration.
  Design and build. The contractor is appointed to both design and build the project. This has the benefit of offering a single point of responsible contact for the client to deal with.
  Single stage. Can be applied to suppliers as well as to the construction part of the contract. All the required information is available to calculate a realistic price at the tendering stage allowing a complete contract to be awarded.

## Slide 9
Types of procurement routes (continued)
  Two stage. A contractor is appointed before all information is available (first stage) so that work can commence and later, when all information is available (second stage), a fixed price for the rest of the work is agreed.
  Lump sum. A ‘lump sum’ price for all the agreed work is finalised before any work commences. This is the more traditional approach to project procurement and is often linked to single stage tendering.

## Slide 10
Managing the contract
  Throughout the project, from the procurement stage through to completion and handover, the contractor must manage cash flow and spending to ensure financial security for its workers and staff.
  The supply chain of suppliers, contractors and sub-contractors rely on the main contractor to competently manage payment periods and deadlines for their own business success and profitability.

## Slide 11
Any questions?