## Slide 1: 5.4 The principles of project management PowerPoint 15: Project management
PowerPoint presentation
5. Business

## Slide 2: Objectives
By the end of this presentation, learners should be able to:
  explain the principles and importance of project management
  discuss the project planning process
  create a project plan with defined purpose and scope
  consider how to implement a project plan
  discuss the project completion and closure process.

## Slide 3: What is project management (PM)?
    Project management (PM) is the process of initiating, planning and utilising all the resources required to bring a specific, one-off, time-constrained goal to a successful conclusion.
    Stages of project management
      Initiate the project.
      Define the project’s purpose.
      Scope the project.
      Write an implementation plan.
      Manage resources.
      Manage risks.
      Monitor and report progress.
    Each project should have a very specific purpose with start and end dates rather than being a constant activity or process.

## Slide 4: Project management – importance
    PM is expensive. Each project requires an investment of time, money and resources. If these are not managed properly, projects fail.
    Why PM is important
      Gives direction and leadership.
      Ensures communication routes.
      Plans budget/contingency needs.
      Sets blueprint to meet milestones.
      Aligns team actions and deliverables.
      Ensures project stays on schedule.
      Reduces risk of failure in project delivery.
      Reports lessons learnt for future projects.
    Good PM practice is vital for businesses to get a return on its investment in the successful implementation of a project and the benefits it can bring.

## Slide 5: Project planning process – structuring projects
    The structure of a project refers to the process of how it is organised and managed.
    A project organisation structure should include:
      decision-making arrangements
      how the project will be achieved
      the project methodology model used
      a plan of how it will be actioned
      budget parameters
      lists of resources, staff, materials and tools
      deliverables and timelines to be agreed
      description of reporting procedures to stakeholders.
    The project organisation structure is created in collaboration with the client and specialists from relevant departments working with the project manager.

## Slide 6: Project management – roles and responsibilities
Generally, each project has three areas of responsibility requiring different kinds of skills and expertise.
Each project management model defines its own roles and responsibilities and may give them different titles, but the areas of responsibility remain the same.
Areas of responsibility
  Project leadership: overall management.
  Project board: decision makers/defines success.
  Project team: specialists implementing the project.

## Slide 7: Project planning process – initiation phase
Initiation is the feasibility testing of a project. Stakeholder discussions consider documents, plans and the purpose of the project before any decision to go ahead is taken.
Initiation phase
  Identify the deliverables: the goals.
  Consider purpose, priorities and constraints.
  Scope what is included and not included.
  Consider risks: resources, budget, time.
  Present project proposal documents to client.
  The project manager will present an overall project proposal. This sets out budgets, timelines and deliverables based on the agreed scope of the project.

## Slide 8: Project planning process – defining purpose
Every project starts as an idea. Before it can begin, there must be a common understanding of its purpose, so everyone involved knows what is expected.
The project purpose should explain:
  the reason the project exists
  the ambition of the project’s success
  the direction it needs to take
  the impact it needs to have.
  A project purpose statement is created outlining the whole project from start to finish. Including the justification for the project, scope, goals, deliverables, exclusions, constraints and assumptions (see Worksheet 15b).
Notes: Tutors’ Note: Example of Project Purpose Statement can be found on Worksheet 15b. This could be used to structure a class discussion or as a template for learners to create their own project purpose statement.

## Slide 9: Project planning process – scope
Scoping a project helps to determine goals, workflow management, tasks to complete and project deliverables.
Project scope
  Sets the roadmap to align actions to goals.
  Manages stakeholder expectations.
  Aids budget management.
  Aids workflow scheduling.
  Prevents scope creep.
  A project scope cannot be set in stone because it needs flexibility to deal with unforeseen issues caused by scope creep. A clearly defined scope statement can help recognise and address issues.

## Slide 10: Project planning process – planning phase
This phase only begins when a project proposal is approved and scoped out.
Project planning phase
  Create a project blueprint: high-level milestones.
  Create a detailed plan of tasks for each milestone.
  Identify team members responsible for each task.
  Include every resource/information point needed.
  Planning is a constant activity throughout a project. If something does not go according to plan, there is a need to readjust and offer alternative solutions.

## Slide 11: Project planning process – setting goals and objectives
SMART is an acronym used to make business and project planning more practical.
SMART
  Specific: asks what, where, who, which, why?
  Measurable: how do I know when it is done?
  Achievable: is it feasible/possible to do this?
  Relevant: is it aligned with strategies/values?
  Time-bound: when does it need to be done by?
  The SMART method ensures project managers and team members are ready to focus their efforts on using resources to increase the chance of completing a successful project.

## Slide 12: SMART – goals vs objectives
Goals and objectives have differences and there are implications for a business or project.
SMART goals | SMART objectives
Longer term desire | Shorter term target
Primary goal – unlikely to be changed | Small steps to move towards the goal – may change over time
Owner’s vision or senior team effort | Divided into tasks for specialist to complete
Strategic viewpoint and plan | Tactical operations that can be adjusted

## Slide 13: Project planning process – setting SMART goals
A goal is the desired state at the end of a time period. Goals can also be SMART.
SMART project goals
  Define the final destination of a project.
  Generic but motivational to achieve.
  Close enough to feel real/feasible.
  Sufficient time to reach them.
  A goal for a business owner may be to open more outlets across the country. The objectives will be what the business needs to achieve to make that a reality.

## Slide 14: Project planning process – setting objectives
An objective is one of the targets that helps achieve the goal.
Look at these SMART objectives for a project to launch a business website.
  Specific: launch website by end of February 20XX.
  Measurable: functioning website by this date.
  Achievable: outsource to a web developer.
  Relevant: to be major online marketing tool.
  Time-bound: complete by 28th February 20XX.
  The project statement could read: ‘I will launch my business website by the end of February 20XX to support my goal of opening more outlets across the country. I will outsource to a skilled web designer/developer and will communicate with them regularly.’

## Slide 15: Project plan implementation
Implementation is when the project team begin the actual work required.
Implementation phase
  Set up tasks in a work breakdown structure.
  Allocate and manage team members.
  Track progress using preferred methodology .
  Monitor critical path of task to ensure no bottlenecks.
  Communicate project progress regularly with clients.
  The project manager will be constantly evaluating and changing where necessary. For example, materials may not be available, team members may leave, objectives may change.

## Slide 16: Project plan implementation – workflow management
Web development project
Initiation
Planning
Implementation
Control
Closure
Idea
Purpose
Statement
Scoping
Project team
Schedule
Budget
Website design
Page design
Photography
Graphic design
Written content
Website build
Set up servers
Build templates
Test site
LAUNCH
Resource management
Cost management
Risk management
Review
Lessons learnt
Project handover
Workflow management breaks down all the tasks that need to be completed and puts them into a visual diagram of the plan known as the work breakdown structure (WBS).

## Slide 17: Project plan implementation – setting realistic milestones
Milestones break the objectives and actions of a project into small sections with a checkpoint for progress. Tasks are identified with deadline dates for completion.
Project milestones
  Set the full timeline for the whole project.
  Identify logical, frequent checkpoints.
  Detail steps and tasks for each milestone.
  Gain stakeholder agreement on milestones.
  Assign each milestone to a person or team.
  Set steps out visually in a GANTT chart or similar.
  For example, the work breakdown structure shows the website project needs to consider more than just outsourcing to a web developer.

## Slide 18: Project plan implementation – workflow management
GANTT charts are a visual representation of the progress of a project over time.
  They set out tasks from start to finish.
  They include schedules and assign project tasks.
  Horizontal structure shows critical path (dependencies).
  Project manager can actively monitor every step of progress.
  The web development project itemises the tasks, shows the milestones, who is responsible for delivery and by when.
  Source: GANTT chart created by Lesley Renwick

## Slide 19: Project constraints
Project constraints are the limitations of a project. They impact on each other, which is why they need to be managed carefully.
Constraints to the scope of a project include:
  Quality
  Cost
  Time.
  There are always trade-offs when balancing these three constraints – what needs to be sacrificed to ensure the project stays aligned and achievable?

## Slide 20: Project constraints
A project stays in scope only if timelines are realistic and budgets are available.
Scope | Cost | Time
Quantity Quality Deliverables | Project cost Salaries Materials Resources Equipment | Project total timeline Hours allocated Diary management Milestones and goals Project phases
Scope creep is caused by lack of clarity in purpose, goals, objectives and project planning detail. | Anything of financial value; affected by scope creep eg something not in original plan/not budgeted for. | Overrun and extending timelines increase costs and potential for scope creep; budget cuts mean time cuts.
Remedy: clients sign off everything before start of project. | Remedy: close monitoring of actual spend against project spend and stop any overspend. | Remedy: set realistic milestones, ensure scope boundaries are maintained.

## Slide 21: Project implementation – completion
When the clients are completely satisfied, it is time to handover the final project including any procedural documents, technical support manuals and instructions.
Completion
  Analyse performance against objectives.
  Lessons learnt and what might be improved.
  Handover all project deliverables to clients.
  Team members and other resources released.
  Here our client is opening another outlet and her website is fully functional.
  Client feedback is collected for use in reviews and marketing.

## Slide 22
Any questions?